## Bug Report
S.No | Bug ID | Module / Page | Page URL | Bug Title | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Device / Browser | Account Used | Wallet Address | Transaction Hash | Screenshot / Video | Status | Assigned To | Reported By | Reported Date | Comments
1 | BUG-001 | Sign Up | https://app.saphercoin.com/sign-up | Premature validation error shown while entering incomplete phone number | Low | Low | 1. Open: https://app.saphercoin.com/sign-up 2. Click on the Phone Number field. 3. Type phone number digits one by one slowly. | Validation message should appear only after a complete invalid phone number is entered — on field blur or form submit. | Application displays 'Invalid phone number' error while the user is still entering partial digits. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-001 | Open | Development Team | Nadeem | 04-Jun-2026 | Reproduced on all tested browsers. Trigger validation on field blur, not on each keystroke.
2 | BUG-002 | Sign Up | https://app.saphercoin.com/sign-up | Phone number field accepts input beyond maximum allowed length | Medium | Medium | 1. Open: https://app.saphercoin.com/sign-up 2. Click the Phone Number field. 3. Enter a phone number exceeding 15 digits. | Phone number field should restrict input to a maximum of 15 digits (E.164 international standard). | Application allows entering more than 15 digits without restriction or truncation. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-002 | Open | Development Team | Nadeem | 04-Jun-2026 | Add maxlength='15' to phone input field. E.164 standard limits to 15 digits for all international numbers.
3 | BUG-003 | Sign Up | https://app.saphercoin.com/sign-up | Inconsistent validation messages shown for oversized phone numbers | Low | Low | 1. Open: https://app.saphercoin.com/sign-up 2. Enter different oversized numbers (16 digits, then 20 digits). 3. Observe the validation message each time. | A single consistent validation message should appear for all invalid phone number formats. | Different messages appear: 'Invalid phone number' for some inputs and 'Invalid format' for others. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-003 | Open | Development Team | Nadeem | 04-Jun-2026 | Standardize all phone validation to one consistent error message across the codebase.
4 | BUG-004 | Sign Up | https://app.saphercoin.com/sign-up | Email field accepts malformed special characters and spaces without validation | Medium | Medium | 1. Open: https://app.saphercoin.com/sign-up 2. Click on the Email Address field. 3. Enter malformed input with spaces and special characters: e.g. 'test @!#.com' 4. Observe whether input is accepted. | Email field should reject malformed input and show an inline validation error. | Email field accepts unsupported special characters and spaces without any validation error. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-004 | Open | Development Team | Nadeem | 04-Jun-2026 | Module corrected: issue is on Sign Up page, not Sign In. Enforce RFC 5322 email format.
5 | BUG-005 | Sign Up | https://app.saphercoin.com/sign-up | Cursor jumps to beginning of email field while deleting malformed input | Low | Low | 1. Open: https://app.saphercoin.com/sign-up 2. Type a malformed email with spaces: 'test user @mail .com' 3. Position cursor at the end of the field. 4. Press Backspace key repeatedly. | Cursor should remain at its current position while deleting text. | Cursor unexpectedly jumps to the beginning of the email field during Backspace deletion. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | N/A | N/A | BUG-005 | Open | Development Team | Nadeem | 04-Jun-2026 | Module corrected: issue on Sign Up page. Cursor jump caused by DOM manipulation during keystroke-level validation.
6 | BUG-006 | Sign Up / Sign In | https://app.saphercoin.com/sign-up | Inconsistent Phone/Mobile terminology used across the authentication flow | Low | Low | 1. Open: https://app.saphercoin.com/sign-up 2. Navigate through the Phone Number registration/login flow. 3. Observe all labels, placeholders, and error messages. | Application should use one consistent term — 'Phone Number' — across all pages and messages. | Different terms: 'Phone', 'Mobile number', and 'Phone number' are used interchangeably. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-006 | Open | Development Team | Nadeem | 04-Jun-2026 | Module corrected. Minor UX inconsistency — standardize to 'Phone Number' throughout all UI text.
7 | BUG-007 | Sign In | https://app.saphercoin.com/login | Application reveals whether a phone number is registered — user enumeration risk | Medium | High | 1. Open: https://app.saphercoin.com/sign-in 2. Select phone login option. 3. Enter a phone number NOT registered in the system. 4. Click 'Send OTP by WhatsApp' or 'Send OTP by SMS'. 5. Observe the error message. | Application should display a generic message: 'Invalid credentials' — without revealing account existence. | Application explicitly displays: 'No user exists with that phone number', confirming the number is unregistered. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-007 | Open | Development Team | Nadeem | 04-Jun-2026 | SECURITY: User enumeration vulnerability. Attacker can verify registered numbers. Use generic 'Invalid credentials' for all auth failures. Priority raised to High.
8 | BUG-008 | Sign In | https://app.saphercoin.com/login | Misleading 'Too many failed attempts' error shown after OTP requests with no failed verification | Medium | Medium | 1. Open: https://app.saphercoin.com/sign-in 2. Enter a valid registered phone number. 3. Click 'Send OTP by SMS' or 'WhatsApp' repeatedly. 4. Do NOT enter or submit any OTP. 5. Observe error message after repeated requests. | Error message should accurately reflect OTP request throttling: 'Too many OTP requests. Please wait.' | Application displays 'Too many failed attempts. Try again later.' even though no OTP was ever entered or failed. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-008 | Open | Development Team | Nadeem | 04-Jun-2026 | Rate limiting works correctly but the error message is inaccurate. Fix message to reflect request throttling, not verification failures.
9 | BUG-009 | Sign In | https://app.saphercoin.com/login | Expired OTP remains valid after expiry and allows successful login | High | High | 1. Open: https://app.saphercoin.com/sign-in 2. Enter a valid registered phone number. 3. Click 'Send OTP by SMS'. 4. Wait until the OTP expiry timer fully elapses. 5. Enter the expired OTP. 6. Click Verify / Login. | Expired OTP should be rejected with message: 'OTP expired. Please request a new OTP.' | Application accepts the expired OTP and successfully logs the user in after the validity period. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-009 | Open | Development Team | Nadeem | 04-Jun-2026 | SECURITY: OTP expiry must be enforced server-side. Client-side only expiry is bypassable. Critical for a financial wallet.
10 | BUG-010 | Sign In | https://app.saphercoin.com/login | Rate limit error persists for different phone numbers after failed OTP attempts on one | High | High | 1. Open: https://app.saphercoin.com/sign-in 2. Enter a valid phone number, request OTP, and enter it incorrectly multiple times. 3. Trigger rate limit error. 4. Click 'Change Number' and enter a completely different phone number. 5. Request OTP again and observe. | Rate limiting should apply per phone number only. A different number should request OTP normally. | Rate limit error 'Too many failed attempts' continues to appear even for the different phone number. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-010 | Open | Development Team | Nadeem | 04-Jun-2026 | Rate limiting applied at session/IP level instead of per phone number. Could block any user on same IP.
11 | BUG-011 | Sign In (Magic Link) | https://app.saphercoin.com/login | Magic link can be reused multiple times — single-use token not enforced | Critical | High | 1. Navigate to sign-in page and request a magic link. 2. Open the email and click the link — login succeeds. 3. Copy the same magic link URL. 4. Paste it in a new browser tab and attempt login again. | Magic link should be invalidated immediately after first successful use. Reuse should show: 'Link already used or expired.' | The same magic link successfully authenticates the user on every subsequent use without expiring. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-011 | Open | Development Team | Nadeem | 04-Jun-2026 | CRITICAL SECURITY: Magic links must be single-use tokens. Reusable link allows unauthorized wallet access if email is intercepted. Severity upgraded to Critical.
12 | BUG-012 | Sign In (Magic Link) | https://app.saphercoin.com/ | Expired magic link remains valid and authenticates user past its expiry duration | Critical | High | 1. Request a magic link from sign-in page. 2. Wait until the full expiry duration has elapsed. 3. Open the same expired magic link from the email. 4. Observe whether authentication succeeds. | Expired magic link should be rejected. Show: 'This link has expired. Please request a new sign-in link.' | Magic link continues to authenticate the user even well past the expected expiry duration. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-012 | Open | Development Team | Nadeem | 04-Jun-2026 | CRITICAL SECURITY: Token expiry must be validated server-side. An indefinitely valid magic link in an inbox is a permanent unauthorized access vector. Severity upgraded to Critical.
13 | BUG-013 | Sign In (Magic Link) | https://app.saphercoin.com/ | Same magic link creates parallel active sessions across multiple browsers simultaneously | Critical | High | 1. Request a magic link and copy its URL from the email. 2. Open the link in Google Chrome — login succeeds. 3. Paste the same link in Mozilla Firefox — login succeeds. 4. Paste the same link in Microsoft Edge — login succeeds. 5. Observe all three sessions are active simultaneously. | Magic link should expire after first successful authentication. Reuse across browsers should be blocked. | Same magic link authenticates in Chrome, Firefox, and Edge — creating three active wallet sessions simultaneously. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | N/A | N/A | BUG-013 | Open | Development Team | Nadeem | 04-Jun-2026 | CRITICAL SECURITY: Related to BUG-011 and BUG-012. Three concurrent wallet sessions from one link. Severity upgraded to Critical.
14 | BUG-014 | Sign In | https://app.saphercoin.com/ | Session remains active after prolonged inactivity — no automatic timeout enforced | Medium | Medium | 1. Login successfully. 2. Leave session idle for more than 30 minutes without any user activity. 3. Refresh the Wallet Dashboard page. 4. Observe whether re-authentication is required. | Session should automatically expire after the inactivity timeout. User should be redirected to login. | Session remains fully active after prolonged inactivity. Dashboard accessible after refresh without re-login. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | N/A | N/A | BUG-014 | Open | Development Team | Nadeem | 04-Jun-2026 | Standard for financial apps is 15-30 min idle timeout. Implement configurable session expiry with warning prompt.
15 | BUG-015 | Sign In | https://app.saphercoin.com/login | Unexpected password breach warning displayed during security boundary testing | Medium | Medium | 1. Open: https://app.saphercoin.com/sign-in 2. Enter SQL injection string in Email: ' OR '1'='1 3. Enter same string in Password. 4. Click the phone icon beside email. 5. Dismiss browser prompt to save password. 6. Click OK on the 'Password found in data breach' pop-up. | Application should display only relevant validation messages for invalid input. | Browser displays unexpected password breach warning during SQL injection boundary testing. | Windows 11 / Chrome 125 | Account 1 | N/A | N/A | BUG-015 | Open | Development Team | Nadeem | 04-Jun-2026 | Triggered by browser password manager during security testing. Review input sanitization to prevent SQL strings from interacting with browser security tools.
16 | BUG-016 | Sign In | https://app.saphercoin.com/login | Inconsistent phone number validation across different international country codes | Medium | Medium | 1. Open: https://app.saphercoin.com/sign-in 2. Select +1 (USA) and enter an 11-digit number. 3. Change to +44 (UK) and enter an 11-digit number. 4. Change to +971 (UAE) and enter an 11-digit number. 5. Compare validation behavior. | Validation should apply country-specific rules per ITU-T E.164 standard for each country code. | +1 (USA) accepts 11-digit numbers, while +44 (UK) and +971 (UAE) reject the same 11-digit format. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-016 | Open | Development Team | Nadeem | 04-Jun-2026 | Use a standard library (e.g. libphonenumber) to handle country-specific validation rules automatically.
17 | BUG-017 | Sign In | https://app.saphercoin.com/login | OTP delivered successfully even after immediate page refresh during request | Medium | Medium | 1. Open: https://app.saphercoin.com/sign-in 2. Enter a valid registered phone number. 3. Click 'Send OTP by SMS' or 'Send OTP by WhatsApp'. 4. Immediately refresh the browser before OTP request completes. 5. Check mobile device for OTP delivery. | OTP request should be safely cancelled on page refresh. Unexpected delivery should not occur. | OTP is still successfully delivered even after the page was refreshed mid-request. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | N/A | N/A | BUG-017 | Open | Development Team | Nadeem | 04-Jun-2026 | OTP backend processing is independent of frontend page state. Minor UX issue. Consider cancelling in-flight OTP requests on page unload.
18 | BUG-018 | Session Management | https://wallet.saphercoin.com/ | Logout from one device does not terminate active sessions on other devices | High | High | 1. Login in Chrome browser with a valid account. 2. Login with the same account in Firefox or mobile browser. 3. Confirm both sessions are active. 4. Logout from Firefox. 5. Return to Chrome, refresh Dashboard. 6. Observe whether Chrome session is still active. | Logout should invalidate session server-side and terminate all active sessions for that account. | Chrome session remains fully active after logout was performed from Firefox. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | N/A | N/A | BUG-018 | Open | Development Team | Nadeem | 04-Jun-2026 | SECURITY: Severity/Priority upgraded to High. Server-side token revocation on logout is essential for a crypto wallet. Implement 'Logout from all devices' option.
19 | BUG-019 | Sign In | https://app.saphercoin.com/login | Previous backend error message persists alongside new client-side validation message | Low | Low | 1. Open: https://app.saphercoin.com/sign-in 2. Enter a valid-format non-existent email: nsdasdkasn@gmail.com 3. Enter any password and click Sign In — observe 'User does not exist' error. 4. Change email to invalid format: nsdasdkasn@@gmail..com 5. Observe all error messages displayed. | When email becomes invalid, only 'Enter a valid email address' should display. Previous backend error should clear. | Both messages appear simultaneously: 'Enter a valid email address' AND 'User does not exist in our records'. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | N/A | N/A | BUG-019 | Open | Development Team | Nadeem | 05-Jun-2026 | Backend error state must be cleared when email field value changes. Error states should be mutually exclusive.
20 | BUG-020 | Reset Password | https://app.saphercoin.com/reset-password | Password field accepts spaces-only input as a valid password | High | High | 1. Login successfully. 2. Navigate to My Account → Reset Password from Wallet Dashboard. 3. Enter only blank spaces (9 spaces) in the New Password field. 4. Enter same blank spaces in Confirm Password field. 5. Observe: 'Passwords match' is shown. 6. Click Update Password. 7. Complete OTP verification. | Application should reject spaces-only passwords with: 'Password cannot contain only spaces.' | Application accepts spaces-only password as valid. OTP completes, password is updated successfully. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 2 | N/A | N/A | BUG-020 | Open | Development Team | Nadeem | 05-Jun-2026 | SECURITY: Apply .trim() + non-empty check before validation. Spaces-only password bypasses all strength checks. Additional observation: 'Changes cancelled' toast also appeared post-update.
21 | BUG-021 | Reset Password / Sign In | https://app.saphercoin.com/reset-password | Spaces-only password set via Reset Password cannot be used to login — inconsistency | Medium | Medium | 1. Login and navigate to Reset Password. 2. Set spaces-only password and complete OTP — success shown. 3. Logout. 4. Go to Sign In page. 5. Attempt login using the same account and spaces-only password. | Password behavior should be consistent. A password accepted in Reset Password must work in Sign In. | Reset Password accepts spaces-only password. Sign In cannot authenticate with same password — account locked out. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 2 | N/A | N/A | BUG-021 | Open | Development Team | Nadeem | 05-Jun-2026 | Direct consequence of BUG-020. Fixing BUG-020 resolves this. Inconsistency can permanently lock users out of wallet.
22 | BUG-022 | Wallet Dashboard | https://wallet.saphercoin.com/ | Wallet address copy toast notification persists during rapid account switching | Low | Low | 1. Login as Account 1 and go to Wallet Dashboard. 2. Click the Copy Wallet Address icon. 3. Observe 'Wallet address copied successfully' toast. 4. Immediately switch to Account 2. 5. Quickly switch back to Account 1. 6. Observe toast behavior. | Copy notification should disappear on account/session switch and not persist across context changes. | Wallet address copy toast from Account 1 remains visible after switching to Account 2 and back. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 & Account 2 | N/A | N/A | BUG-022 | Open | Development Team | Nadeem | 05-Jun-2026 | Toast notification state not cleared on account switch. Add cleanup on component unmount or account change event.
23 | BUG-023 | Wallet Dashboard | https://wallet.saphercoin.com/database/transfercoin | Lock icon on Transaction page navigates to Wallet page instead of performing lock action | Low | Low | 1. Login to the application. 2. Navigate to My Transaction from Wallet Dashboard. 3. Locate the Lock icon in the top-right corner of the Wallet Address section. 4. Click the Lock icon. 5. Observe application behavior. | Lock icon should perform a lock or security-related action on the wallet. | Clicking the Lock icon redirects the user to the Wallet page instead of performing any lock action. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | N/A | N/A | BUG-023 | Open | Development Team | Nadeem | 05-Jun-2026 | Incorrect navigation route assigned to Lock icon. Review UI component routing and map the correct lock action handler.
24 | BUG-024 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Wallet address field accepts special characters and spaces without validation | Medium | Medium | 1. Login to the application. 2. Click My Wallet from Wallet Dashboard. 3. Locate the TO ADDRESS field on Transfer Coin page. 4. Enter special characters and spaces: ~!@#$%^&*()_+{}¦:"<>?`-=[];',./ 5. Observe whether input is accepted. | Wallet address field should accept only valid blockchain format: 0x + 40 hex characters. All else rejected. | Field accepts spaces and unsupported special characters before any validation occurs. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | Account 1 Wallet Address | N/A | BUG-024 | Open | Development Team | Nadeem | 05-Jun-2026 | Enforce regex: /^0x[0-9a-fA-F]{40}$/ on wallet address field. Fixed typo 'Dahsboard' in steps.
25 | BUG-025 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Wallet address field accepts input exceeding the 42-character maximum limit | Medium | Medium | 1. Login to the application. 2. Click My Wallet from Wallet Dashboard. 3. Locate the TO ADDRESS field on Transfer Coin page. 4. Enter a wallet address longer than 42 characters. 5. Observe whether length restriction is enforced. | Field should restrict input to exactly 42 characters (0x + 40 hex chars). | Application accepts addresses exceeding 42 characters without restriction or error. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | Account 1 Wallet Address | N/A | BUG-025 | Open | Development Team | Nadeem | 05-Jun-2026 | Add maxlength='42' to wallet address input and enforce server-side length validation too.
26 | BUG-026 | Blockchain Explorer | https://explorer.sapherchain.com/ | Plural grammar error: '1 days ago' displayed instead of '1 day ago' | Low | Low | 1. Open: https://explorer.sapherchain.com/ 2. Click on Transactions tab. 3. Search transaction: 0x21cd7783e1FD4F24B2f673750b77750c454C5133 4. Scroll down to the transactions table. 5. Observe the Days column on the left. | Application should display '1 day ago' (singular) for single-day timestamps. | Application incorrectly displays '1 days ago' — wrong plural for a singular value. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 2 | N/A | 0x21cd7783e1FD4F24B2f673750b77750c454C5133 | BUG-026 | Open | Development Team | Nadeem | 05-Jun-2026 | Apply: value === 1 ? 'day' : 'days'. Same fix needed for hours, minutes, seconds throughout explorer.
27 | BUG-027 | Blockchain Explorer | https://explorer.sapherchain.com/ | SAPH Whitepaper footer link returns 404 Page Not Found | Medium | Medium | 1. Open: https://explorer.sapherchain.com/ 2. Scroll to the footer section. 3. Locate the 'SAPH Whitepaper' link. 4. Click the link. 5. Observe the result. | Whitepaper link should open the SAPH Whitepaper document or page successfully. | Application redirects to a broken page: '404 Page Not Found'. Whitepaper is inaccessible. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | N/A | N/A | BUG-027 | Open | Development Team | Nadeem | 05-Jun-2026 | Severity corrected to Medium (was High). Broken link to Whitepaper — critical trust document for a blockchain product. Fix or remove until ready.
28 | BUG-028 | Blockchain Explorer | https://sapherchain.com/ | 'Back to Home' button on 404 page redirects to a different website domain | Medium | Medium | 1. Open: https://explorer.sapherchain.com/ 2. Click the SAPH Whitepaper link in the footer (see BUG-027). 3. On the 404 error page, click 'Back to Home'. 4. Observe the redirect destination. | 'Back to Home' should redirect to the SapherCoin domain: https://explorer.sapherchain.com | User is redirected to an unrelated different domain instead of the application. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | N/A | N/A | BUG-028 | Open | Development Team | Nadeem | 05-Jun-2026 | Wrong home URL configured in the 404 page template. Update 'Back to Home' to the correct app homepage.
29 | BUG-029 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Amount field accepts invalid special characters: e, E, +, and minus symbols | Medium | Medium | 1. Login to the application. 2. Click My Wallet from Wallet Dashboard. 3. Locate the AMOUNT TO SEND field. 4. Enter values: e, E, +, -, ++, -- one by one. 5. Observe whether accepted. | Amount field should accept only valid positive numeric values. e, E, +, - should be blocked. | Amount field accepts all listed invalid characters without any validation error. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | Account 1 Wallet Address | N/A | BUG-029 | Open | Development Team | Nadeem | 05-Jun-2026 | HTML input type='number' allows e/E/+/- by default. Block via onKeyDown event handler. Fixed typo 'Dahsboard' in steps.
30 | BUG-030 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Scientific notation value '1e5' accepted in the coin amount field | Medium | Medium | 1. Login to the application. 2. Click My Wallet from Wallet Dashboard. 3. Locate the AMOUNT TO SEND field. 4. Enter: 1e5 5. Observe whether accepted and if Send Coin button activates. | Application should reject scientific notation. Only plain decimal values should be accepted. | Value '1e5' is accepted and Send Coin button becomes active — treating it as 100,000. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | Account 1 Wallet Address | N/A | BUG-030 | Open | Development Team | Nadeem | 05-Jun-2026 | 1e5 = 100,000 in JS. Could bypass balance checks. Block 'e' and 'E' keys explicitly. Fixed typo 'Dahsboard' in steps.
31 | BUG-031 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Excessive leading zeros accepted in amount field without normalization | Low | Low | 1. Login to the application. 2. Click My Wallet from Wallet Dashboard. 3. Enter a valid receiver wallet address. 4. Enter amount: 00000000000000000000000000000001 5. Click Send Coin. | Amount field should normalize or reject leading zero input. Displayed value should show as '1'. | Amount with excessive leading zeros is accepted and transaction processes as '1 SAPH'. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | Account 1 Wallet Address | N/A | BUG-031 | Open | Development Team | Nadeem | 05-Jun-2026 | Transaction processes correctly but input lacks normalization. Add parseFloat() on input. Fixed typo 'Dahsboard' in steps.
32 | BUG-032 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Transaction completes successfully even after browser page refresh during processing | High | High | 1. Login to the application. 2. Click My Wallet from Wallet Dashboard. 3. Enter receiver: 0x21cd7783e1FD4F24B2f673750b77750c454C5133 4. Enter amount: 0.001 SAPH 5. Click Send Coin. 6. Immediately refresh the browser page. 7. Check wallet balances and transaction history. | Page refresh should safely cancel the pending transaction OR maintain a pending state. Double processing must not occur. | Transaction continues and completes successfully even after the page is refreshed mid-process. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 & Account 2 | Account 1 Wallet Address | See screenshot — hash recorded post-transfer | BUG-032 | Open | Development Team | Nadeem | 06-Jun-2026 | Implement idempotency key per transaction to prevent double-processing. Lock transaction state once broadcast.
33 | BUG-033 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Wallet balance mismatch after successful transfer — financial discrepancy on dashboard | Critical | High | 1. Login as Account 1 — note sender balance: 1.81964 SAPH 2. Login as Account 2 in another browser — note receiver balance: 0.169254 SAPH 3. From Account 1, enter Account 2 wallet address. 4. Enter transfer amount: 0.5 SAPH 5. Click Send Coin — wait for successful completion. 6. Check Account 1 balance. 7. Check Account 2 balance. 8. Verify on blockchain explorer. | After 0.5 SAPH transfer: Account 1: 1.81964 - 0.5 = 1.31964 SAPH Account 2: 0.169254 + 0.5 = 0.669254 SAPH Balances must be mathematically consistent with transfer amount. | Account 1 shows: 1.31922 SAPH (expected: 1.31964) — gap: 0.00042 SAPH Account 2 shows: 0.67254 SAPH (expected: 0.669254) — gap: 0.003286 SAPH No fee breakdown shown to explain discrepancy. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 & Account 2 | Account 1 Wallet (Sender) ¦ Account 2 Wallet (Receiver) | See screenshot — 0.5 SAPH transfer hash recorded | BUG-033 | Open | Development Team | Nadeem | 06-Jun-2026 | CRITICAL: Severity upgraded. Financial discrepancy likely from undisclosed gas fee. App MUST show full fee breakdown before and after every transaction. Verified on explorer — discrepancy confirmed.
34 | BUG-034 | Wallet Dashboard | https://wallet.saphercoin.com/ | Multiple copy notifications stack on rapid wallet address icon clicks | Low | Low | 1. Login to the application. 2. Navigate to Wallet Dashboard. 3. Rapidly click the wallet address copy icon multiple times. 4. Observe toast notification behavior. | Only one copy notification should display at a time regardless of click speed. | Multiple 'Wallet address copied successfully' toasts stack on top of each other. | Windows 11 / Chrome 125, Firefox 126, Edge 125 Android 16 / Chrome Mobile, Firefox Mobile | Account 1 | Account 1 Wallet Address | N/A | BUG-034 | Open | Development Team | Nadeem | 06-Jun-2026 | Add click debounce to the copy icon. Use a singleton toast manager — dismiss existing toast before showing new one.
35 | BUG-035 | Transaction History | https://wallet.saphercoin.com/database/transactionhistory | Truncated transaction hash copied from UI — full hash not retrievable | Medium | Medium | 1. Login to the application. 2. Navigate to My Transaction / Transaction History. 3. Locate a completed transaction with a visible hash. 4. Click the copy icon next to the hash. 5. Paste into blockchain explorer search. 6. Observe results. | Full 66-character transaction hash (0x + 64 hex chars) should be copied to clipboard. | Only the truncated display version (e.g., 0x1234...5678) is copied. Explorer search returns no results. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | Account 1 Wallet Address | See transaction history — full hash in screenshot | BUG-035 | Open | Development Team | Nadeem | 06-Jun-2026 | Copy action reads displayed truncated text. Store full hash in a data attribute and copy from that.
36 | BUG-036 | Blockchain Explorer | https://explorer.sapherchain.com/ | Address Insights 'Last Active' shows incorrect duration — not reflecting latest transaction | Low | Low | 1. Open: https://explorer.sapherchain.com/ 2. Search for a recently active wallet address. 3. Note the timestamp of the most recent transaction. 4. Compare with the 'Last Active' value in Address Insights. | 'Last Active' should reflect time elapsed since the most recent transaction for that address. | 'Last Active' shows '5 days ago' even though recent transactions exist for the address within hours. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 2 | Account 2 Wallet Address | N/A | BUG-036 | Open | Development Team | Nadeem | 06-Jun-2026 | 'Last Active' sourced from account creation date instead of MAX(transaction_timestamp). Query latest tx timestamp.
37 | BUG-037 | Transaction Search | https://wallet.saphercoin.com/database/transactionhistory | Partial transaction hash with leading/trailing spaces still returns search results | Low | Low | 1. Login to the application. 2. Navigate to My Transaction from Wallet Dashboard. 3. Copy a valid transaction hash. 4. Remove characters from both ends to make it partial. 5. Add spaces before and after. 6. Paste into search field and click Search. | Application should trim whitespace before search. Partial hashes should not return results — exact match required. | Partial transaction hash with leading and trailing spaces is still searchable and returns results. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | Account 1 Wallet Address | N/A | BUG-037 | Open | Development Team | Nadeem | 06-Jun-2026 | Apply .trim() before API call. Enforce exact hash match for transaction lookup to prevent data exposure.
38 | BUG-038 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Full wallet balance transfer allowed without reserving blockchain gas fee | High | High | 1. Login to the application. 2. Click My Wallet from Wallet Dashboard. 3. Note available balance (e.g. 1.31922 SAPH). 4. Enter a valid receiver wallet address. 5. Enter the exact full balance: 1.31922 SAPH 6. Click Send Coin. 7. Observe result. | App should prevent sending full balance without gas reserve. Show max transferable: balance - gas fee. | App allows full balance input and enables Send Coin. After submit: 'Transaction Failed! Insufficient funds for gas.' | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 2 | Account 2 Wallet Address | N/A — transaction failed | BUG-038 | Open | Development Team | Nadeem | 06-Jun-2026 | Pre-calculate max sendable = balance - estimated gas. Display 'Max: X SAPH' in form. Fixed typo 'Dahsboard' in steps.
39 | BUG-039 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Transaction loader stuck indefinitely when internet is disconnected during processing | High | High | 1. Login to the application. 2. Click My Wallet from Wallet Dashboard. 3. Enter valid receiver address and amount. 4. Click Send Coin. 5. Immediately disable internet connection. 6. Observe the transaction state for several minutes. | App should detect network failure and show: error message, timeout fallback, or retry option. | App displays 'Sending... Processing your transaction' indefinitely. No timeout, error, or retry shown. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 2 | Account 2 Wallet Address | N/A — transaction did not complete | BUG-039 | Open | Development Team | Nadeem | 06-Jun-2026 | Implement 60-second transaction timeout. Show: 'Transaction timed out — check history before retrying.' Fixed typo 'Dahsboard'.
40 | BUG-040 | Coin Transfer | https://wallet.saphercoin.com/database/transfercoin | Transaction resumes and completes automatically after internet reconnection without user confirmation | Medium | High | 1. Login as Account 1. 2. Navigate to My Wallet. 3. Enter valid receiver address and amount. 4. Click Send Coin. 5. Immediately disable internet. 6. Observe stuck loader (see BUG-039). 7. Re-enable internet. 8. Observe what happens to the pending transaction. | After reconnect, show recovery prompt: 'Connection restored. Would you like to retry this transaction? [Retry] [Cancel]' | Transaction automatically resumes and completes without any user confirmation, retry prompt, or notification. | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 2 | Account 2 Wallet Address | See screenshot — hash recorded post-reconnect | BUG-040 | Open | Development Team | Nadeem | 06-Jun-2026 | Financial transactions must not auto-resume without explicit user action. Add confirmation before resuming pending txn.
41 | BUG-041 | Blockchain Explorer | https://explorer.sapherchain.com/tx/123 | Explorer exposes raw internal error message for invalid transaction hash URL | Medium | Medium | 1. Open directly: https://explorer.sapherchain.com/tx/123 2. Observe the page displayed. | Explorer should show a friendly message: 'Transaction not found' or 'Invalid transaction hash format.' | Explorer displays raw internal error: 'Error loading transaction data: An error occurred' | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | N/A | 123 (invalid — for testing) | BUG-041 | Open | Development Team | Nadeem | 06-Jun-2026 | Add error boundary. Validate hash format (/^0x[0-9a-fA-F]{64}$/) before API call. Show user-friendly 'not found' page.
42 | BUG-042 | Blockchain Explorer | https://explorer.sapherchain.com/address/0x123 | Explorer accepts and renders page for invalid wallet address format | Medium | Medium | 1. Open directly: https://explorer.sapherchain.com/address/0x123 2. Observe page behavior. | Explorer should validate address format before lookup. Show: 'Invalid wallet address' or 'Address not found.' | Explorer accepts invalid address and renders page showing: 'Unable to load address details' | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | 0x123 (invalid — for testing) | N/A | BUG-042 | Open | Development Team | Nadeem | 06-Jun-2026 | Validate format /^0x[0-9a-fA-F]{40}$/ before API call. Prevents unnecessary requests and improves UX.
43 | BUG-043 | Coin Transfer / API | https://wallet.saphercoin.com/database/transfercoin | Repeated 401 Unauthorized API errors generated in console during transfer and refresh | Medium | Medium | 1. Open Browser Developer Tools (F12). 2. Go to Console or Network tab. 3. Login to the application. 4. Perform wallet transfer operations. 5. Refresh page during or after transfer. 6. Observe console/network logs. | Console should be free from repeated auth errors during normal application usage. | Console repeatedly shows: 'GET https://backend-auth.enopsy.com/api/auth/client/me 401 (Unauthorized)' | Windows 11 / Chrome 125, Firefox 126, Edge 125 | Account 1 | Account 1 Wallet Address | N/A | BUG-043 | Open | Development Team | Nadeem | 06-Jun-2026 | Auth token not refreshing. Implement token refresh interceptor. Note: backend domain (backend-auth.enopsy.com) exposed in client logs — security review needed.

## Test Summary
SapherCoin.com — Testing Report Summary
Project Name | SapherCoin.com
Company | Sapher AllHeart Pvt Ltd
Application URL | https://app.saphercoin.com
Explorer URL | https://explorer.sapherchain.com
Tester | Nadeem
Testing Types | Functional · Session · Authentication · API · Blockchain · UI/UX · Network
Browsers Tested | Chrome 125, Firefox 126, Edge 125, Chrome Mobile, Firefox Mobile
Platforms Tested | Windows 11, Android 16
Test Period | 29 May 2026 – 07 Jun 2026
Total Bugs Found | 43
Final Testing Status | ❌ FAILED — Critical security and financial issues identified
Bug Count by Severity
Severity | Count | % of Total | Description
Critical | 4 | 9% | Auth security & financial integrity — must fix before release
High | 7 | 16% | Major functional and security issues
Medium | 20 | 47% | Incorrect output, input validation, and UX issues
Low | 12 | 28% | UI inconsistencies and cosmetic issues
Bug Count by Module
Module | Bugs | Notes
Sign Up | 6 | Validation and input handling issues
Sign In | 9 | OTP, magic link, and authentication security
Sign In – Magic Link | 3 | 3 Critical bugs — single-use token not enforced
Session Management | 1 | Logout does not terminate all active sessions
Reset Password | 2 | Spaces-only password accepted — account lockout risk
Wallet Dashboard | 3 | Toast and UI navigation issues
Coin Transfer | 11 | Highest bug count — core feature impacted
Transaction History / Search | 3 | Hash copy and search validation issues
Blockchain Explorer | 5 | Error handling and display accuracy issues
Critical Bugs — Must Fix Before Go-Live
Bug ID | Module | Issue
BUG-011 | Sign In (Magic Link) | Magic link reusable multiple times — unauthorized wallet access risk
BUG-012 | Sign In (Magic Link) | Expired magic link authenticates user — permanent access vector in inbox
BUG-013 | Sign In (Magic Link) | Same magic link creates parallel sessions across all browsers
BUG-033 | Coin Transfer | Wallet balance mismatch after transfer — financial discrepancy confirmed
Testing Coverage
Account Creation & Email Verification | ✅ Tested
Email / Phone OTP Login Flow | ✅ Tested
Magic Link Authentication | ✅ Tested
Session Management & Logout | ✅ Tested
Password Reset Flow | ✅ Tested
Wallet Dashboard & Address Display | ✅ Tested
Coin Transfer — Happy Path | ✅ Tested
Coin Transfer — Boundary & Negative Cases | ✅ Tested
Transaction History & Hash Verification | ✅ Tested
Blockchain Explorer Lookup | ✅ Tested
Network Interruption Handling | ✅ Tested
Browser Console / API Error Monitoring | ✅ Tested

## Legend & Guide
Field Guide — How to Read This Bug Report
FIELD | DESCRIPTION
S.No | Sequential number 1–43. Never reused even after a bug is closed.
Bug ID | BUG-XXX format, 3-digit zero-padded. Permanent reference ID.
Module / Page | App section/module where the bug was found.
Page URL | Exact URL where the bug was observed during testing.
Bug Title | One clear sentence — what is wrong and where.
Severity | CRITICAL = Financial/security impact ¦ HIGH = Major feature broken MEDIUM = Incorrect output ¦ LOW = UI/cosmetic issue
Priority | HIGH = Fix immediately ¦ MEDIUM = Fix next sprint ¦ LOW = When time allows
Steps to Reproduce | Numbered steps to reproduce the exact bug from scratch.
Expected Result | What SHOULD happen per requirements or common sense.
Actual Result | What ACTUALLY happens — include exact error messages.
Device / Browser | Browser version + OS used during testing.
Account Used | Account 1, Account 2, or both — which triggered the bug.
Wallet Address | Wallet address(es) involved in the test. N/A if not applicable.
Transaction Hash | Blockchain TxHash if transfer executed. N/A if not applicable.
Screenshot / Video | File reference — see screenshots/ folder in repository.
Status | Open → In Progress → Fixed → Retest → Closed / Reopen
Assigned To | Team responsible for fixing. Update per team structure.
Reported By | Tester name.
Reported Date | DD-Mon-YYYY format.
Comments | Security notes, fix suggestions, reproduction rate, related bug IDs.
SEVERITY vs PRIORITY
Severity = impact on the user | Critical security bug nobody found yet = High Severity, Low Priority
Priority = urgency to fix | Login bug blocking all users = Medium Severity, High Priority
CORRECTIONS APPLIED IN THIS VERSION
Module fixed | BUG-004, BUG-005 corrected from Sign In → Sign Up
Module fixed | BUG-006 corrected to Sign Up / Sign In
Severity upgraded | BUG-011, 012, 013 upgraded to Critical (magic link auth failures)
Severity upgraded | BUG-033 upgraded to Critical (financial data integrity)
Severity upgraded | BUG-018 upgraded to High/High (session security)
Severity corrected | BUG-027 adjusted to Medium/Medium (broken link only)
Priority raised | BUG-007 Priority raised to High (user enumeration)
Typos fixed | 'Wallet Dahsboard' corrected to 'Wallet Dashboard' in all steps
Date format fixed | Dates corrected from serial numbers to readable DD-Mon-YYYY
Screenshot format | Fixed from 'BUG-XXX' to proper file path references
3 new columns added | Page URL ¦ Wallet Address ¦ Transaction Hash (per test doc spec)
Comments completed | All 43 bugs now have meaningful technical context in Comments
Summary updated | Added Critical category with correct counts after all corrections